## RAID Log
RAID Log Tracker
|  |  | IF AN ISSUE, ASSUMPTION OR DEPENDENCY, COMPLETE THIS SECTION |  | IF A RISK, COMPLETE THIS SECTION For risk grading guidance, see separate tab
RAID Type | Summary description | Date raised | Priority level Auto RAG setting | Status | Impact | Likelihood | RAG status Auto populated | Risk status | Planned action(s) If accepting, monitoring or tolerating a risk, please give reason why | Owner | Target date | Progress notes & any closing comments | Date closed
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Hidden cells below - please do not delete
Risk |  |  | High | Not started | 1 | 1 |  | Accept
Assumption |  |  | Medium | On track | 2 | 2 |  | Avoid
Issue |  |  | Low | Behind schedule | 3 | 3 |  | Mitigate
Dependency |  |  |  | Resolved | 4 | 4 |  | Monitor
|  |  |  | Closed | 5 | 5 |  | Tolerate
Removed

## Log definitions
RAID Log
Column Title | Definition | Notes
RAID Type | Risk (R) - an event or situation that may happen, but which can be prevented or limited by taking action to reduce or avoid the chance of that event or situation happening Assumption (A) - an educated guess in absence of facts used to take action on a project assumption being made due to facts being unavailable. Important to record and manage any assumptions that, if proven incorrect, would have an adverse impact on the project e.g. its timeframe, costs, scope and/or the quality of what is due to be delivered. Issue (I) - a problem, event or situation that has occurred and needs action taken to be resolved and to avoid it recurring. Dependency (D) - an influence on the project that may adversely impact its timeframe, costs, scope and/or the quality of what is due to be delivered. A dependency can be either internal within the project or external to the project (e.g. reliance on another project or a third party) | Risks must also be recorded in the Trust's risk management system, Datix. Rules around when to raise a Datix or not to be clarified by Louise Arnett
Summary Description | An informative, brief summary outlining the situation needing to be resolved or managed. | Any further detail required should be described elsewhere if necessary, for example in an options paper/SBAR or in Datix if it is a risk
Date raised | Date that the item was raised | This will help track how long items have been open for
Priority level | High priority items should be highlighted in Project Board meetings and Highlight Reports. When the priority level is selected, a RAG colour will automatically be applied. | This must be completed for Assumptions, Issues and Dependencies (please leave blank for risks).
Status | Used for tracking progress on them - whether 'not started', 'on track', 'behind schedule', 'resolved' or 'closed'. Used for governance reporting. | This must be completed for Assumptions, Issues and Dependencies (please leave blank for risks).
Impact | Please see Risk Grading tab for a guide to how to grade the potential consequence of the risk coming to fruition | To be completed for Risks only.
Likelihood | Please see Risk Grading tab for a guide to how to grade the chances of the risk coming to fruition | To be completed for Risks only.
RAG status | This field will automatically calculate the risk level based upon the impact and likelihood gradings you have applied. This field will convert the calculated risk level into a RAG status. This field will auto populate, so no need to fill it in manually. | Applicable to Risks only.
Risk status | It is important to be clear on how the risk will be managed: Monitor - the Trust / Project Board accepts the risk, so no specific actions will be taken; however, the Project Manager must monitor the risk in case the situation changes Mitigate - specific actions are required to reduce the risk in a situation where the risk cannot be avoided entirely Accept - the Trust / Project Board accepts the risk and does not require it to be monitored by the project. It may be that the risk is monitored away from the project or closed or deferred for review at a later date beyond the lifetime of the project Avoid - specific actions are required to avoid and remove the risk where possible Tolerate - the Trust / Project Board are willing to wait for a period of time and tolerate risk until resolving action becomes available (e.g. long term strategic solution is becoming available that will remove the risk). Removed - the risk is no longer relevant to the projects due to changing circumstances | Applicable to Risks only.
Planned actions | Please state the specific actions that will be taken to address the RAID type. For risks specifically, if actions help to reduce the risk level, the log item should be updated to reflect the changing impact and likelihood levels. If the risk level is rising, the log must also be updated to reflect this, particularly if the resulting RAG status requires escalating to Project Board. For the others, the priority level should be adjusted if actions reduce the priority status or inaction increases the priority.
Owner | State who will own the action(s) and be responsible for ensuring that actions are being progressed and completed.
Target date | Please provide target end dates for completing actions. The dates may need to be driven by business need and agreed project plan/timescales.
Progress notes and any closing comments | Any progress that has been made on actions planned and current status. | Please precede comments with the date notated (e.g. "10/05: action X was completed") and consider the chronological order of those dated notes, so that the latest notes always show at the top.
Date closed | Date that the Project Manager or Board agrees that the situation at hand has been addressed. Who makes the decision depends upon RAG status.

## Purpose & Guide
RAID Log
The log is a tool designed to: - help project managers identify and assess risks to be mitigated, assumptions needing to be validated with facts, issues needing to be resolved, and dependencies to be accounted for in project plans. - focus upon RAID items that will adversely affect the boundaries of your project (time, cost, quality, scope) if they are not carefully managed. - record and manage all items threatening the success of the project in one central log. - track what action is needed, by whom and by when. It is designed to promote action and ensure people take responsibility and ownership of actions to enable the project to be successful in achieving its objective and desired outcomes. The Project Manager is expected to maintain the log and oversee the progression and management of the items within. Ownership of actions will, however, sit across roles within the project team and, where appropriate, within project board or even outside of the project.
The RAID log must be created upon project initiation. It is advisable that the Project Manager hold a workshop with their project team, key stakeholders and project board members where appropriate to identify any risks, issues, assumptions and dependencies that could threaten the success of the project The log should be used as a 'living' tool through the lifetime of the project. High priority and risk level items are particularly important to manage through the log and to highlight where they need to be escalated to the Project Board (or higher through Executive committees within the Trust's Integrated Governance Framework) for consideration. To create an audit trail, it is advisable to version control the RAID log periodically. Keeping previous versions - showing RAID items at a particular point in time during the project's lifetime - can provide a useful reference point, particularly for lessons learned.

## Risk grading
RAID Log
Impact or Consequence
|  | 1 | 2 | 3 | 4 | 5
| Likelihood | None | Minor | Moderate | Major | Catastrophic
5 | Will undoubtably occur or recur, possibly frequently
4 | Will probably occur or recur, but not a persistent issue
3 | May occur or may recur occasionally
2 | Do not expect it to happen (again), but it is possible
1 | Cannot believe that this will ever happen (again)
More detailed guidance on risk grading can be found as an appendix within the Trust's Risk Management Policy:
http://intranet/website/staff/policies/businessandprovisionofservices/riskmanagementpolicyandprocedure.asp
The Trust's strategy for risk management can be found under:
http://intranet/website/staff/policies/businessandprovisionofservices/riskmanagementstrategy.asp
The Trust's strategy aligns with Wiltshire CCG's Risk Management Strategy, which can be found under:
http://www.wiltshireccg.nhs.uk/about-us/risk-management