## Risk Log
|  |  | Name | Nexus Workgroup
Last Updated
Category | Risk ID | Title/Area | Area | Description of Risk | Cause \ Factors | Impact | Risk Proximity Start Date | Risk Proximity End Date | Impact Date | Date Identified | Identified By | Gross Risk Value (£) | Probability (P) | Impact (I) | Score (P*I) | Risk Owner | Mitigation Actions | Mitigation Action Date (s) \ Target Resolution | Mitigating Action Owner | Residual Risk Value (£) | Probability (P) | Impact (I) | Score (P*I) | Issue Ref No. | Status | Status Date | Date Closed
|  |  |  | There is a risk that......... | because of.......... | leading to.....
| RIS001 | EU Reform | Settlement | There is a risk that the EU changes may impact the implementation date of the Nexus changes | because of the extent & complexity of the changes required to industry systems, including Gemini | leading to a delay in the delivery of the new Settlement arrangements and Nexus requirements | 2013-10-01 | 2015-10-01 | 2015-10-01 | 2013-09-30 | NGT |  | 3 | 5 | 15 | NGT | Impact assessment on changes required to gemini for both UU changes and Nexus | 2014-06-01 | NGT |  |  |  |  | ISS001 | Awaiting Approval

## Assumptions Log
| Name | Nexus Workgroup
Last Updated
Assumption Reference | Cross Topics Y/N | Assumption Description | Comments | Proximity Start Date | Proximity End Date | Raised by | Date Raised | To be Agreed by | Date Agreed | Review Date | Status | Status Date
ASS | [10 empty] | Open

## Issue Log
|  | Name | Nexus Workgroup
Last Updated
Issue Ref | Title | Area | Description of Issue and its Impact | Date Identified | Identified By | Priority (MoSCoW) | Impact (Severity) Rating | Owner | Issue Resolution Actions | Responsible for Action | Target Resolution Date | Resolution Date | Cost of Action (£) | Status | Status Date | Open Days
ISS001 | EU Reform | Settlement | EU are making changes to the Daily Settlement processes effective from 1st October 2015 which will require changes to Gemini | 2013-09-01 | PN UNC | Must | 4 | NGT | 1. Xoserve to carry out impact assessment | Xoserve | 2014-06-01 |  |  | Raised

## Dependency Log
Name | Nexus Workgroup
Last Updated
Dependency Reference | Title | Description (to include who dependency is on Internal / External) | Date Required | Owner | Forecast Completion Date | Actual Completion Date | Impact of missed completion date | Comments | Status | Status Date
DEP001

## Info
Information relating to RAID proforma
Proximity | A start and end date should be documented which details the period of time over which the risk may be experienced
Risk Probability Scoring Matrix: | Score | Probability of Occurrence | Description
| 1 | <= 10% | Remote
| 2 | >10% <= 40% | Less Likely
| 3 | >40% <= 60% | Equally as likely as unlikely
| 4 | >60% <= 90% | More likely
| 5 | >90% | Almost certain
Risk Impact Scoring Methodology | Impact | Very Low (1) | Low (2) | Medium (3) | High (4) | Very High (5)
| Financial | x < £100,000 | £100,000 < x < £500k | £500k < x < £1 million | £1 million < x < £2 million | X > £2 million
| Reputation | Minor impact on Project | Major impact on Project | Minor impact on Project & 1 Stakeholder | Major impact on Project & a Stakeholder group | Major impact on Project & all stakeholders
MoSCoW: | M | Must
| S | Should
| C | Could
| W | Won't

## Governance
Definition: Risk: | An uncertain event or set of events that, should it occir, will have an effect on the achievement of objectives
A Risk is something that may happen in the future
Definition: Issue: | A relevant event that has happened, was not planned, and which requires action.
Issues can be problems, benefits or situations
An Issue is something that is happening now
Process: | 1. The Risk / Issue/ Assumption / Dependency raised by an individual or at PN UNC
2. If raised outside of PN UNC, the relevant proforma is submitted to the Joint Office for publishing for discussion at the following meeting
3. The item is discussed & agreed in the Workgroup:
a) Agree information & scoring
b) Assign ownership
c) Agree any actions
4. Monitor each item at the Workgroups
a)Updates where appropriate Any further actions agreed
b) Closed by approval of PN UNC
Responsibilities: | Joint Office: | Maintaining the RAID Log
| Nexus Workgroup: | Record Risks, Issues, Assumptions & Dependencies
| Nexus Workgroup: | Review & manage
| Nexus Workgroup: | Agree ownership & actions
| Anyone: | Review Risks, Issues, Assumptions & Dependencies
| Owners: | Take appropriate & agreed actions

## Requirements
ID | Date Raised | Status | Heading | BRD / Topic | Area | Options | Actions/Resolution | Agreed Date
REQ1 | 2013-10-30 | Open | Read Validation | Settlement | Following a transfer of ownership the new Shipper will be unable to validate the first read received from a consumer as they will have no history. | Send new Shipper the lastest read before the transfer effective date. | The latest read at D-7 will be sent to the Proposing Shipper. Not included in Mod 0432. Needs to be added to BRD & a Modification
REQ2 | 2013-11-19 | Open | Winter Consumption | AQ | WAR Bands are derived annually for Monthly Read sites (AQ greater 293,000kWh) using the consumption derived from reads loaded during the preceding years winter consumption. Currently there is an appeal process where Shippers can challenge the WAR band | Propose to follow the same principle as the AQ review process: No appeals process, the winter consumption is based on the validated reads loaded & WAR band applied based on the consumption. | To be agreed at 08/01/2014 meeting
REQ3 | 2013-11-22 | Open | Duplicates | SPR | Process improvement for notifying & processing a duplicate MPRN